## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered
Sprint 1 | Activity | Story points
Diagrams | context Diagram | 2
| use case | 1
| Activity diagram | 2
| Sequence Diagram for ordering | 2
| class Diagram for different coffe types | 1
| Draw data model | 2
| Total | 10
|  |  | Velocity Sprint 1 | 6
Story Points
Sprint 2 | Front _end design | 3
Login/Reg | Backend_Design | 3
| Total | 6
|  |  | Velocity Sprint 2 | 6
Sprint 3 | Requirements | 3
HomePage | Front_end Design | 3
Backend :
| view products | 2
| filter menu based on drink type | 3
| Total | 11
|  |  | Velocity sprint 3 | 11
Sprint 4
Place order | Front_end Design | 4
Backend :
| order details | 2
| filter menu based on drink type | 3
| add drink | 1
| confirm order | 1
| Past order details | 2
| Total | 13 | Velocity Sprint 4 | 9
sprint 5
admin | front_end Design | 3
Backend:
| update/delete product/find | 3
| add product | 4
| customers | 3
| Total | 13 | Velocity Sprint | 10
Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Another option
Burndown Chart | Remaining Story Points | Story Points Delivered
Sprints
1 | 53 | 6
2 | 47 | 6
3 | 41 | 11
4 | 36 | 9
5 | 27 | 0